## READ ME
Construction Schedule Template
A working schedule in Excel, and a 10-point check of how healthy it is
| WHAT IT IS | A construction schedule you can build and update in Excel: activities, durations, a simple finish-to-start link to one predecessor, a Gantt chart that redraws itself, progress against a status date, and a status for every activity. The second sheet is a 10-point check of the schedule's health.
| START HERE | 1. On the Schedule sheet, enter the project name, the project start date and the status date (the date your progress is measured to). 2. Delete the example rows (Hartwell Commercial Centre) or overwrite them. 3. For each activity enter an ID, the WBS code, the name and the duration in working days. Use 0 for a milestone. 4. In Predecessor, type the ID of the activity it must follow. The predecessor must be listed above it. 5. Each update period, change the status date and enter % complete for the work in progress.
| HOW DATES WORK | Start = the next working day after the predecessor finishes, or the project start if there is no predecessor. "Start no earlier than" pushes an activity later when you need it. Working days are Monday to Friday; public holidays are not deducted. Yellow cells are yours to fill in; grey cells calculate.
| STATUS | Complete = 100%. Late = finish date has passed and the work is not complete. Behind = more than 10 points below the progress expected by the status date. In progress and Not started are what they say.
| WHAT EXCEL CANNOT DO | This template follows one predecessor per activity and has no float, no critical path and no baseline. Look at A210 in the example: practical completion really depends on three activities, but Excel can only follow one. That is the point where a spreadsheet stops being a schedule.
| NEXT STEP | When the project needs logic between several activities, the critical path, a baseline and a monthly report without learning MS Project or Primavera, use the Project Scheduler. It reads this kind of schedule from Excel.
Open the Project Scheduler demo — schedule.pmtoolsbyapm.com
| © LICENCE | © 2026 PM Tools by a PM. Licensed for personal and professional use on your own projects. Not for resale, redistribution or upload to any other marketplace.
| SUPPORT | Questions? Email support@pmtoolsbyapm.com. We reply within one business day.
PM Tools by a PM · Construction Schedule Template · pmtoolsbyapm.com

## Schedule
CONSTRUCTION SCHEDULE TEMPLATE
Plan, update and report a project schedule in Excel · free from PM Tools by a PM
Project |  | Hartwell Commercial Centre — Phase 1 |  |  |  | Project start | 2025-06-02 |  | Status date | 2025-10-15
|  | FORECAST FINISH |  | % COMPLETE (by duration) |  | ACTIVITIES BEHIND OR LATE |  | ACTIVITIES
Gantt: ■ planned ■ done ■ late ◆ milestone ¦ status week
ID | WBS | Activity | Duration (working days) | Predecessor (ID above) | Start no earlier than | Start | Finish | % complete | Status | Notes
A010 | 1.1 | Notice to proceed | 0 |  |  |  |  | 100%
A020 | 1.2 | Mobilisation and site setup | 8 | A010 |  |  |  | 100%
A030 | 2.1 | Excavation and earthworks | 12 | A020 |  |  |  | 100%
A040 | 2.2 | Foundations and ground beams | 15 | A030 |  |  |  | 100%
A050 | 3.1 | Ground floor slab | 8 | A040 |  |  |  | 100%
A060 | 3.2 | Structural frame, levels 1–3 | 28 | A050 |  |  |  | 100%
A070 | 3.3 | Roof structure | 8 | A060 |  |  |  | 100%
A080 | 3.4 | Frame topped out | 0 | A070 |  |  |  | 100%
A090 | 4.1 | Roofing and waterproofing | 10 | A080 |  |  |  | 100%
A100 | 4.2 | Cladding and windows | 30 | A080 |  |  |  | 40% |  | Cladding supplier two weeks late
A110 | 5.1 | MEP first fix, level 1 | 15 | A080 |  |  |  | 90% |  | Short of electricians
A120 | 5.2 | MEP first fix, levels 2–3 | 20 | A110 |  |  |  | 10%
A130 | 6.1 | Blockwork and partitions | 20 | A110 |  |  |  | 15%
A140 | 6.2 | Plastering and ceilings | 20 | A130 |  |  |  | 0%
A150 | 5.3 | MEP second fix | 15 | A140 |  |  |  | 0%
A160 | 6.3 | Floor and wall finishes | 20 | A140 |  |  |  | 0%
A170 | 6.4 | Painting and decoration | 15 | A160 |  |  |  | 0%
A180 | 7.1 | External works and parking | 25 | A100 |  |  |  | 0%
A190 | 8.1 | Testing and commissioning | 10 | A150 |  |  |  | 0%
A200 | 8.2 | Snagging | 8 | A170 |  |  |  | 0%
A210 | 8.3 | Practical completion | 0 | A200 |  |  |  | 0% |  | Also depends on A180 and A190 — Excel can follow only one predecessor
PM Tools by a PM · Construction Schedule Template · pmtoolsbyapm.com
Formulas:
ACTIVITIES BEHIND OR LATE = IF([FORECAST FINISH]="","",IFERROR(WORKDAY(MAX(N(F9),IF(E9="",ProjStart,WORKDAY(INDEX(H8:H8,MATCH(E9,A8:A8,0)),1)))-1,1),"Check ID"))

## Health Check
SCHEDULE HEALTH CHECK · 10 POINTS
Answer each question honestly. A score under 8 means the schedule needs attention before you report from it.
# | Check | Why it matters | Your answer | Score | Project Scheduler
1 | Every activity has a predecessor and a successor, apart from the first and the last. | An activity with no successor can slip without moving the finish date. The schedule then hides the delay instead of showing it. |  |  | ✓ Checked automatically
2 | No activity is longer than about two update periods (roughly 20 working days). | Long activities hide progress. By the time they show a problem, it is too late to recover. |  |  | ✓ Checked automatically
3 | Lags are few, positive and explained. | Unexplained lags are often padding or a fix for missing logic. Reviewers and Engineers treat them as a warning sign. |  |  | ✓ Checked automatically
4 | Dates come from logic, not typed in (hard constraints are rare and justified). | A typed date never moves. If the work before it slips, the schedule stays falsely on time. |  |  | Your call
5 | A baseline was saved and agreed. | Without a baseline you cannot show slippage, and you cannot defend an extension of time. |  |  | Your call
6 | There is a status date, and nothing planned sits in the past without an actual date. | Planned work left before the status date means the update was not done. The forecast is then wrong from the start. |  |  | ✓ Checked automatically
7 | % complete reflects physical progress, not time elapsed or money spent. | Time-based progress makes every activity look on track until the day it is late. |  |  | ✓ Checked automatically
8 | The critical path runs continuously from start to finish and makes sense on site. | A broken critical path means the logic is incomplete. You may be managing the wrong activities. |  |  | ✓ Checked automatically
9 | Activities with 5 days of float or less are listed and watched. | Next month's critical path comes from today's near-critical work, not from today's critical path. |  |  | ✓ Checked automatically
10 | Key milestones match the contract dates, and the forecast finish is compared with the contract completion. | The client and the Engineer judge the project against the contract, not against your plan. |  |  | Your call
SCORE (out of 10)
VERDICT
When the project needs logic between several activities, the critical path, a baseline and a monthly report without learning MS Project or Primavera, use the Project Scheduler. It reads this kind of schedule from Excel.
Open the Project Scheduler demo — schedule.pmtoolsbyapm.com
PM Tools by a PM · Construction Schedule Template · pmtoolsbyapm.com

## Lists (hidden)
status | answers
Complete | Yes
In progress | Partly
Not started | No
Behind
Late