## Read Me
RISK REGISTER
Construction · Oil & Gas · Manufacturing ¦ PM Tools by a PM ¦ Version 1.0
WHAT THIS IS
A risk register is not a list of things that might go wrong. It is a management tool: it forces you to quantify exposure, assign an owner to every risk, and prove that the exposure came down because someone did something about it.
This workbook gives you the structure and the scoring engine. The risks themselves are yours to identify — they are specific to your project, your contract, and your site.
HOW TO USE IT
1. Go to the "Risk Register" tab. Row 5 is a worked example — delete it once you understand the format.
2. Fill in the shaded (pale yellow) columns only. Every white column is a formula and will calculate itself.
3. Score Probability and each Impact dimension from 1 to 5 using the scales below. Use the dropdowns.
4. The register calculates Inherent Score, Residual Score, and their ratings automatically.
5. Check the "Heat Map" tab — it counts your risks by band and shows where your exposure sits.
6. Review it weekly. A register updated once at tender stage and never again is worse than no register, because it creates the appearance of control without the substance.
WRITING A RISK PROPERLY — CAUSE → EVENT → EFFECT
This is the single biggest difference between a register that works and one that does not.
A risk written as "Bad weather" is useless. You cannot own it, mitigate it, or measure it. Write it as three linked parts:
PART | CAUSE (because of...) | EVENT (this may happen...) | EFFECT (resulting in...)
WEAK | — | "Bad weather" | —
STRONG | Because the site sits in a cyclone belt and works are scheduled through the wet season | concrete pours to the upper deck may be suspended for extended periods | resulting in delay to the critical path and standing time for the concrete gang and pump.
The strong version tells you what to monitor (the forecast), who owns it (the concrete subcontractor and the planner), what it costs (standing time, quantified), and whether a contract notice is required. The weak version tells you nothing.
PROBABILITY SCALE (1 – 5)
SCORE | RATING | DEFINITION
5 | Almost Certain | > 80% — expected to occur; has already occurred on this project
4 | Likely | 60 – 80% — has occurred on similar projects; conditions are present
3 | Possible | 40 – 60% — could occur; no strong indicators either way
2 | Unlikely | 20 – 40% — would require an unusual combination of circumstances
1 | Rare | < 20% — theoretically possible; no realistic pathway identified
IMPACT SCALE (1 – 5) — score each dimension separately
SCORE | RATING | COST | TIME | QUALITY / HSE
5 | Severe | > 5% of contract value | > 8 weeks to critical path | Fatality, or defect requiring demolition
4 | Major | 2 – 5% of contract value | 4 – 8 weeks to critical path | Lost-time injury, or major rework
3 | Moderate | 0.5 – 2% of contract value | 1 – 4 weeks to critical path | Medical treatment case, or NCR requiring rework
2 | Minor | 0.1 – 0.5% of contract value | < 1 week; float absorbed | First aid case, or minor NCR
1 | Negligible | < 0.1% of contract value | No effect on critical path | No injury; no quality effect
Adjust the cost thresholds to your contract value before you start. A 5% impact on a $2m job and a $200m job are very different conversations. These bands are a starting point, not a standard.
SCORE BANDS — Score = Probability × Highest Impact
SCORE | BAND | REQUIRED ACTION
15 – 25 | CRITICAL | Escalate now. Requires an owner at PM/Director level and an active response plan. Report to the Employer.
10 – 14 | HIGH | Active mitigation required with a named owner and due date. Review weekly.
5 – 9 | MEDIUM | Manage through normal project controls. Review monthly.
1 – 4 | LOW | Accept and monitor. Review at each register update.
THE COLUMN MOST REGISTERS DO NOT HAVE
Column X — "Contract Notice Required?"
A risk that materialises is no longer a risk. It is an event — and under FIDIC, an event that affects time or cost carries a notice obligation with a deadline measured from the moment you became aware of it. Clause 20.1 gives you 28 days.
The register is very often the document that proves when you became aware. If a risk is sitting on your register with a probability of 4, you are on notice. Use this column to flag, at the point of identification, which contract clause will be engaged if the risk lands — so that when it does, nobody is reading the contract for the first time under time pressure.
CELL LEGEND
Pale yellow — you fill this in
White — calculated automatically. Do not overwrite.
Created by PM Tools by a PM · Engineer, PMP · 20+ years in Construction, Oil & Gas, Manufacturing · Latin America, USA, Caribbean
support@pmtoolsbyapm.com · pmtoolsbyapm.com · © 2026
This template reflects standard FIDIC 1999 conditions. Particular Conditions may modify notice and record obligations — always check your specific contract. This document does not constitute legal advice.

## Lists (hidden)
Category | Score | Strategy | Status | NoticeReq
Design | 1 | Avoid | Open | Yes — notice served
Procurement | 2 | Transfer | In Progress | Yes — notice due
Construction | 3 | Mitigate | Closed | To be assessed
Subcontractor | 4 | Accept | Realised | No
Commercial / Contract | 5 | Exploit | Superseded
Programme / Schedule
HSE
Quality
Permits / Approvals
Site Conditions
Weather / Environmental
Client / Employer
Resource / Labour
Plant / Equipment
Logistics
Commissioning
External / Political
Financial / FX

## Risk Register
PROJECT RISK REGISTER
Project: |  |  |  | Contract No.: |  |  |  |  | Register Date: | [6 empty] | Prepared / Reviewed by:
Risk ID | Date Raised | Category | Risk Description (Cause → Event → Effect) | Trigger / Early Warning Sign | Prob. (1-5) | Impact Cost | Impact Time | Impact Qual/HSE | Max Impact | Inherent Score | Inherent Rating | Response Strategy | Mitigation / Response Actions | Owner | Action Due Date | Resid. Prob. | Resid. Impact | Residual Score | Residual Rating | Score Reduction | Status | Last Reviewed | Contract Notice Required? | Clause Ref. & Notes
R-001 | 2026-03-02 | Programme / Schedule | Because the Employer has not yet confirmed the access route to the north platform, and the piling rig is scheduled to mobilise on 14 March, the rig may arrive with no viable access, resulting in standing time for the rig and crew and delay to the piling sequence on the critical path. | Access route still unconfirmed 7 days before rig mobilisation date. | 4 | 3 | 4 | 1 | 4 | 16 | CRITICAL | Mitigate | 1. Issue written request to Engineer for access confirmation, ref. Clause 2.1, by 05 Mar. 2. Identify alternative southern access and price the diversion. 3. Insert 5-day hold in rig mobilisation subject to confirmation by 09 Mar. | J. Ramirez — Site Manager | 2026-03-09 | 2 | 3 | 6 | MEDIUM | 10 | Open | 2026-03-02 | Yes — notice due | Cl. 2.1 (Right of Access). If access not given by 14 Mar, Clause 20.1 notice due within 28 days of awareness. Awareness date = 02 Mar.
Note on J4: Calculated: the highest of the three impact scores. Risk is driven by its worst dimension, not the average.
Note on K4: Calculated: Probability x Max Impact. This is your exposure BEFORE mitigation.
Note on S4: Calculated: Residual Probability x Residual Impact. Exposure AFTER your mitigation works. If this equals the inherent score, your mitigation is doing nothing.
Note on X4: If this risk materialises, does a contract notice fall due? Under FIDIC Clause 20.1 the 28-day clock runs from awareness. Decide the clause now, not on the day.

## Heat Map
RISK HEAT MAP
Counts update automatically from the Risk Register tab. Inherent exposure (before mitigation).
PROBABILITY | 0 | 0 | 0 | 0 | 0 | 5 Almost Certain
| 0 | 0 | 0 | 1 | 0 | 4 Likely
| 0 | 0 | 0 | 0 | 0 | 3 Possible
| 0 | 0 | 0 | 0 | 0 | 2 Unlikely
| 0 | 0 | 0 | 0 | 0 | 1 Rare
| 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Severe
IMPACT (highest of Cost / Time / Quality-HSE)
REGISTER SUMMARY
Total risks identified |  |  | 1
Critical (15 – 25) |  |  | 1
High (10 – 14) |  |  | 0
Medium (5 – 9) |  |  | 0
Low (1 – 4) |  |  | 0
Open |  |  | 1
Contract notice due |  |  | 1
Avg. score reduction |  |  | 10
Reading the map: risks in the red zone are not "someone should look at that." They are the reason the project will or will not deliver. If your register has no red, either the project is unusually benign — or nobody has scored honestly.
PM Tools by a PM · support@pmtoolsbyapm.com · pmtoolsbyapm.com · © 2026